## Gantt Chart
Name of the project: |  | CORRADI-BOT: Plataforma multicanal con IA para democratizar el acceso a oportunidades Erasmus+ para jovenes
Coordinator: |  | Proactive Future (E10304913 - ES)
Duration: |  | 14 months (September 2026 - October 2027)
PROJECT TIMETABLE
Activity | Title / Sub-activity | Leader | M1 Sep 26 | M2 Oct 26 | M3 Nov 26 | M4 Dec 26 | M5 Jan 27 | M6 Feb 27 | M7 Mar 27 | M8 Apr 27 | M9 May 27 | M10 Jun 27 | M11 Jul 27 | M12 Aug 27 | M13 Sep 27 | M14 Oct 27
A1 | Gestion y coordinacion | Proactive Future
Kick-off meeting
Monthly Steering Committee meetings
Intermediate report (M7) / Final report (M14)
A2 | Investigacion y diseno tecnico | Proactive Future
User needs research (30-50 interviews)
Ecosystem mapping & benchmarking
Technical architecture & UX/UI design
A3 | Desarrollo de la plataforma | Proactive Future
Phase 1: Infrastructure (EC2, Docker, PostgreSQL, Redis)
Phase 2: Chatbot engine (LLM, RAG, Telegram, WhatsApp)
Phase 3: Ingestion system & admin workflow
Phase 4: User features, web catalog, admin panel
Phase 5: Mobile app (React Native + Expo)
Phase 6: Beta testing (150-200 users, 3 countries)
A4 | Difusion y comunidad | LIFE
Dissemination strategy & web launch
Social media campaigns & content production
Monthly newsletter & community management
A5 | Training Course: Formacion IA | LIFE
Curriculum design & materials development
Training sessions Spain (2 sessions, Oviedo)
Training sessions Romania (2 sessions, Bucharest)
Training sessions Greece (2 sessions, Athens)
A6 | Toolkit de Acceso Digital Juvenil | DreamTeam
Content development (methodology, technical guide)
Translation to 4 languages & design
Publication as OER (Creative Commons)
A7 | Eventos multiplicadores | DreamTeam
Event Spain (Oviedo, 30+ participants)
Event Romania (Bucharest, 30+ participants)
Event Greece (Athens, 30+ participants)
BUDGET SUMMARY
Activity | Leader | Budget (EUR)
A1. Gestion y coordinacion | Proactive Future | 10000
A2. Investigacion y diseno tecnico | Proactive Future | 6000
A3. Desarrollo de la plataforma | Proactive Future | 18000
A4. Difusion y comunidad | LIFE | 5000
A5. Training Course: Formacion IA | LIFE | 10000
A6. Toolkit de Acceso Digital Juvenil | DreamTeam | 6000
A7. Eventos multiplicadores | DreamTeam | 9000
TOTAL |  | 64000
LEGEND
A1 - Gestion y coordinacion
A2 - Investigacion y diseno tecnico
A3 - Desarrollo de la plataforma
A4 - Difusion y comunidad
A5 - Training Course: Formacion IA
A6 - Toolkit de Acceso Digital Juvenil
A7 - Eventos multiplicadores